## Cover Page
Clinical Safety Hazard Log - DMRS Release 2
Programme |  | Document Record ID Key
Sub-Prog / Project
Prog. Director |  | Status | Final version
Owner | Steve Bentley | Version | 1
Author |  | Version Date | 2025-02-03
Clinical Safety Hazard Log - DMRS Release 2
Document Purpose
Copyright © 2018, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 19.03.24 | First draft
0.2 | 26.03.24 | Updated following review by CSO
0.3 | 24.10.24 | Updated following review by NHSE Clinical Safety Group
0.4 | 16.01.23 | Updated following review by NHSE Clinical Safety Group
1 | 03.02.25 | Finalised following NHSE Clinical Safety Group Approval
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Pearl Tawana |  | Safety Engineer - NHSE Clinical Safety Group | 2025-01-30 | 0.4
Sebastian Alexander |  | Safety Engineer - NHSE Clinical Safety Group | 2025-01-30 | 0.4
Pearl Tawana |  | Safety Engineer - NHSE Clinical Safety Group | 2024-12-16 | 0.3
Sebastian Alexander |  | Safety Engineer - NHSE Clinical Safety Group | 2024-12-16 | 0.3
Steve Bentley |  | Clinical Safety Officer | 2024-11-21 | 0.3
Pearl Tawana |  | Safety Engineer - NHSE Clinical Safety Group | 2024-09-12 | 0.2
Sebastian Alexander |  | Safety Engineer - NHSE Clinical Safety Group | 2024-09-13 | 0.2
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
NHSE Clinical Safety Group |  | NHSE Clinical Safety Group | 2025-01-30 | 0.4
Steve Bentley |  | Clinical Safety Officer | 2024-11-21 | 0.3
DMRS Project Board |  | Project Board | 2024-03-26 | 0.2
PRSB Assurance Committtee |  | PRSB Assurance Committtee
Distribution
NHS England Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS England corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard Log
|  | Hazard Assessment | [5 empty] | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description | [5 empty] | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[8 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Previous hazard | Previous Harm | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PRSB_NS1a | 07.03.24 | Important information is not available The care professional has to care for the patient without all of the information regarding that patient being available | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | If a system only implements the data items included in this information standard then it will not contain a complete record of a patient as this standard is only a part of the patient record. |  |  | In guidance documentation accompanying the standard it is made clear that the standard does not define the whole of a clinical record - but part of the record defined by the scope of the standard. | See the standard's documentation | N/A |  | N/A |  | Major | Medium | 3 |  | Suppliers/implementers should read the guidance before implementing a standard | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS1b |  |  |  |  | In development of the information standard, critical information for a use case was not identified and therefore not included in the standard. |  |  | In development of a standard the PRSB goes through extensive consultation with stakeholders including open consultations. | See the standard's documentation | N/A |  | N/A |  | Major | Very Low | 2 |  | Suppliers/implementors are responsible for the safety of the systems being used. Any critical deficits should be identified and reported to PRSB. | [5 empty] | Major | Very Low | 2 |  | System suppliers | Transferred
PRSB_NS1c |  |  |  |  | When implementing the standard, local implementers do not implement support for all of the data elements in a standard. This may be due to a local decision on the importance of certain data items. |  |  | The standard uses compliance statements - specifying which data items are mandatory, required or optional. Compliance testing process. PRSB develops a minimum viable product specification for each standard and these form part of the standard documentation. | See the standard's documentation | N/A |  | N/A |  | Major | Medium | 3 |  | Suppliers could put their system through the PRSB standards conformance process. Suppliers/implementors are responsible for the safety of the systems being used | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS1d |  |  |  |  | The standards are complex and are misunderstood and therefore not fully implemented. |  |  | PRSB offers implementation guidance with examples and conducts compliance assessments for providers and suppliers. It also engages in targeted campaigns, presentations, and outreach to suppliers, clinical staff, and patients. | See the standard's documentation | N/A |  | N/A |  | Major | Medium | 3 |  | Suppliers/implementers should read the guidance before implementing a standard Suppliers could put their system through the PRSB standards conformance process. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS1e |  |  |  |  | The information as defined in the standard is not able to be recorded in the source systems or is recorded in a different way, or not structured. So the information may not be available to the user. |  |  | The PRSB standard defines the information which should be collected and available to the user. | See the standard's documentation |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. Suppliers could put their system through the PRSB standards conformance process. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS1f |  |  |  |  | The user is unable to view information which is held in multimedia files e.g. About me. |  |  | The standard defines that particular information such as About Me is important to be understood by any care professional involved in a persons care. | About Me standard documentation | Knowledge of about me |  |  |  | Considerable | Medium | 3 |  | The IT system should be designed to promote important information and provide ready access to it. | [5 empty] | Considerable | Low | 2 |  | System suppliers | Transferred
Overall PRSB_NS1 | [13 empty] | Major | Medium | 3 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_NS2a | 07.03.24 | Poor data quality Information in the care information system is of poor quality. It is incomplete, incorrect, out of date or inconsistent. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | Information in the system is not updated and therefore becomes out dated and potentially contradictory |  |  | All data items included in the standard have associated dates. Information of the same type can be identified using the data structures in the standard. Thus allowing sorting of the data to allow users to interpret the information appropriately | Part of the standard |  |  |  |  | Major | Medium | 3 |  | IT systems should be designed to enable searching and sorting of data elements to enable the viewing of similar information types together. Elements of the record - such as Medications, Allergies and The Problem list should be managed as a single list. |  | User training should include view the information in sortable/searchable lists. Training should include the management of Medications, Allergies, and the Problem list. |  |  |  | Major | Low | 3 |  | System suppliers and service providers | Transferred
PRSB_NS2b |  |  |  |  | Lack of context and provenance of data items may make them appear contradictory |  |  | The standards include definition of context and provenance information | Part of the standard |  |  |  |  | Major | Low | 3 |  | IT systems should maintain the context of data elements where ever possible | [5 empty] | Major | Very Low | 2 |  | System suppliers | Transferred
PRSB_NS2c |  |  |  |  | Inconsistency in recording of information by different care professionals in different systems. |  |  | The standard aims to minimise this by introduction of standard data items | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Providing standardised templates with constrained vocabularies for data entry |  | User training and understanding of the information being recorded. With regular reviews. This should be managed by system suppliers or service providers. |  |  |  | Major | Very Low | 2 |  | System suppliers and service providers | Transferred
PRSB_NS2d |  |  |  |  | Too many mandatory data items may adversely affect data quality by increasing the burden on care professionals. |  |  | PRSB defines data items which are Mandatory/Required/optional for users to populate. Mandatory items are kept to a minimum to deliver safe care. | Part of the standard |  |  |  |  | Major | Low | 3 |  | IT Systems should be designed to auto-populate data fields when ever appropriate. Local implementers can define mandatory fields | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS2e |  |  |  |  | Change in information requirement of a standard. E.g. change in statutory requirements, change in policy or practice in response to COVID-19 pandemic |  |  | The PRSB will, wherever possible review its standards in response to a change in the requirements. Updating the standards where appropriate. | Default review period for PRSB standards is 3 years. A maintenance release can be done at any point and can come earlier for a range of reasons including: Critical safety issue, Build up of significant issues in the maintenance log, Significant changes to other PRSB standards and the need to update to keep alignment Significant changes to policy, legal or the environment around the standard impacting the information requirements. PRSB has a support and maintenance service. Users, Suppliers, Policy teams etcc. are able to raise issues to this service. https://theprsb.org/standards/support/ |  |  |  |  | Major | Low | 3 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_NS2f |  |  |  |  | Failure to adopt PRSB information standards |  |  | The PRSB takes it's standards through the information standards process (DAPB). The outcome of which is an ISN which mandates the implementation of a standard. PRSB supports the implementation of the standards with implementation guidance. PRSB supports the implementation of standards via the Standards Partnership Scheme and conformance process PRSB engagement with system suppliers and provider organisation, | see the standards documentation and ISN see https://theprsb.org/partnerscheme/ |  |  |  |  | Major | Medium | 3 |  | Suppliers should implement PRSB standards. Implementers of IT systems should ensure that the systems they deploy are compliant with PRSB standards. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS2g |  |  |  |  | PRSB standards are updated periodically which may result in changes to the structure or name of sections or elements |  |  | PRSB standards are updated in response to changes in requirements - these changes are clearly recorded and distributed to suppliers and implementors | [5 empty] | Major | Low | 3 |  | Suppliers and implementors should update to the latest version of the standard as soon as possible. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
Overall PRSB_NS2 | [13 empty] | Major | Medium | 3 | [7 empty] | Major | Low | 3 |  |  | Transferred
PRSB_NS3a | 07.03.24 | Important data not found or incorrectly interpreted Critical data in the system is hard to locate, missed, misinterpreted or represented incorrectly. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | Unclear which sections should contain specific information. |  |  | PRSB standards contain descriptions and definitions of the information to be included in specific data elements. Examples and use cases further help to specify these. Specific vocabularies - SNOMED CT or NHS Data dictionary further guide. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors are responsible for the safety of the systems being used. System suppliers should use good user inface design principles to help users to find the information they need. | [5 empty] | Major | Medium | 3 |  | System suppliers | Transferred
PRSB_NS3b |  |  |  |  | The data may have been entered into the wrong section of the record by mistake e.g. Reasonable adjustments or allergy information inappropriately included in the About Me, or not correctly populated. |  |  | PRSB standards contain descriptions and definitions of the information to be included in specific data elements. Examples and use cases further help to specify these. Specific vocabularies - SNOMED CT or NHS Data dictionary further guide. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | The system should allow users to have the ability to edit data been entered into the patient record. |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Low | 3 |  | System suppliers and service providers | Transferred
PRSB_NS3c |  |  |  |  | Blank fields may be misinterpreted. There is a lack of clarity over what a blank field signifies (i.e. not recorded, not assessed, not present, etc). |  |  | PRSB guidance states that for mandatory data item, this data item must be included and a null entry included if there is no information. For required or optional data items, if there is no information then these data items should not be recorded. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients. Including the interpretation of missing information. |  |  |  | Major | Low | 3 |  | System suppliers and service providers | Transferred
PRSB_NS3d |  |  |  |  | Different systems and data structures, semantics and language and processes across different settings and users which may lead to incorrect interpretation / translation of clinical information |  |  | The standard aims to bring together a common representation of the data across the many systems involved. Engagement with clinical terminologist will ensure defined codes will be included in the implementation guidance. E,g, SNOMED CT parent concepts will be defined for each data item, when available. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers/implementors should implement the standard as defined. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS3e |  |  |  |  | Information not found because of volume of data / information overload - critical data such as significant problems or allergies could be missed. |  |  | PRSB carried extensive consultation in the development of the standard to define the essential information to be captured. PRSB defines data items which are Mandatory/Required/optional for users to populate. Mandatory items are kept to a minimum to deliver safe care. | Part of the standard |  |  |  |  | Major | Low | 3 |  | Good user interface design. Local deployment template design |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Low | 3 |  | System suppliers and service providers | Transferred
PRSB_NS3f |  |  |  |  | Inability to determine where, when and by whom clinical information was recorded means the context is lost |  |  | PRSB provenance data support the recording of the where when and who - which can support the linkage of documents/pictures to the record. | Part of the standard |  |  |  |  | Major | Low | 3 |  | Suppliers/implementors should implement the standard as defined. |  |  |  | Systems to record information at point of care by the person giving care. |  | Major | Very Low | 2 |  | System suppliers | Transferred
PRSB_NS3g |  |  |  |  | Clinician unclear about the purpose of some of the information |  |  | The standard has data definitions. Extensive consultation - high level of user recognition and understanding of approach. | Part of the standard |  |  |  |  | Major | Medium | 3 |  |  |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Low | 3 |  | Service providers | Transferred
PRSB_NS3h |  |  |  |  | Sections with unstructured data such as 'About Me' can not be easily found in searches and therefore not reviewed in a timely manner |  |  | Text sections such as "About me" can be indexed using Record Artifact SNOMED CT codes. This will allow these section to be retrieved and displayed in IT systems. These are currently not available for all text sections. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Implement the usage of these Record Artifact SNOMED CT codes. Where not available local codes could be used. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS3i |  |  |  |  | Unfamiliar context/terminology to patients/ service users used in populating the information. |  |  | The standard links to national policies. PRSB carried out extensive consultation with clinicians and the standard is designed to accommodate current practices. | Part of the standard |  |  |  |  | Major | Low | 3 |  |  |  | Users should be trained to understand the terminology used in their IT systems. Users should be given support in understanding the use of terminology in their systems. |  |  |  | Major | Low | 3 |  | Service providers | Transferred
PRSB_NS3j |  |  |  |  | Different statutory and legal requirements across the four UK countries that may lead to confusion by clinicians about which sections are relevant to the country in which they work. |  |  | Standard is designed to be generic as much as possible to accommodate national and local implementation | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers and implementers of the standards should ensure that the systems are compliant with the statutory and legal requirements of the country which the system is deployed | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
Overall PRSB_NS3 | [13 empty] | Major | Medium | 3 | [7 empty] | Major | Medium | 3 |  |  | Transferred
PRSB_NS4a | 07.03.24 | Poor data quality - due to SNOMED CT and other vocabulary content. Information in the care information system is of poor quality. It is incomplete, incorrect, or inconsistent. | Inappropriate/delayed or wrong care given to the patient | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | There is not an appropriate code/ term available for the information that needs to be expressed so local codes are developed |  |  | The standard will include the provision of appropriate codes for data items completion with new codes requested by the NHS England's terminology team where not available. SNOMED CT content can be updated in response to requests for change. | PRSB has a helpdesk to respond to issues with the standards https://theprsb.org/standards/support/ |  |  |  |  | Major | High | 4 |  | PRSB has support and maintenance service to log issues. Local systems running data quality searches. Many systems use standard templates which help users find the appropriate SNOMED CT codes |  | Users should be adequately trained in the safe use of the systems they use to provide care to patients |  |  |  | Major | Medium | 3 |  | System suppliers and service providers | Transferred
PRSB_NS4b |  |  |  |  | Process for creating nationally agreed codes is difficult. |  |  | PRSB works closely with the UK Terminology service to ensure that all the terminology content required to implement the standards are available. | [5 empty] | Major | Medium | 3 | This would only occur if PRSB was not aware that specific terminology was not available | Suppliers and implementers of standards should assure that the required SNOMED CT codes are available in their systems. As new standards will always require new Terminology content to be created, suppliers and implementers must ensure that they have the latest releases of SNOMED CT available. | [5 empty] | Major | Very Low | 2 |  | System suppliers | Transferred
PRSB_NS4c |  |  |  |  | Some suppliers and care providers systems make extensive use of their own local codes. |  |  | PRSB attempts to include all the SNOMED CT concepts required for suppliers to implement the standards. Thus minimising the use of local codes | Part of the standard |  |  |  |  | Major | Medium | 3 |  | Suppliers and implementers of standards should notify the PRSB if there are codes which they require to implement the standards. PRSB can then ensure that these codes are available in the national UK release | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS4d |  |  |  |  | SNOMED CT is dynamic with frequent updates. PRSB may not be up to date with the latest changes to SNOMED CT. |  |  | PRSB will review the SNOMED CT content of standards regularly. Some SNOMED CT vocabularies will be identified as SNOMED CT reference sets - theses will be updated as part of the SNOMED CT release process. | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers of standards should assure; They are able to process concepts which are retired - (i.e. were part of the standard at some time in the past). That they update to the latest version of SNOMED CT as soon as possible. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS4e |  |  |  |  | Some providers are not updating to the latest versions of SNOMED CT |  |  | PRSB recommends that suppliers update to the latest version of SNOMED CT as soon as possible | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers of standards should assure that they update their systems to the latest version of SNOMED CT as soon as possible. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS4f |  |  |  |  | Codes can become inactive and moved or not retained creating difficulty in retrieving historic information. |  |  | PRSB will review the SNOMED CT content of standards when they are upgraded. Some SNOMED CT vocabularies will be identified as SNOMED CT reference sets - theses will be updated as part of the SNOMED CT release process. | [5 empty] | Major | Medium | 3 |  | Suppliers and implementers of standards should assure that they are able to process SNOMED CT content which becomes inactive in an appropriate manner. | [5 empty] | Major | Low | 3 |  | System suppliers | Transferred
PRSB_NS4g |  |  |  |  | A Value set/reference set belongs to third party who no longer updates it. No identified owner for a value set or reference set. |  |  | The SNOMED CT refset management process identifies owners for reference sets - when reference sets are no longer owned these are then retired. As part of the standards management process the SNOMED CT content is reviewed and updated with active content including reference sets. | [5 empty] | Major | Medium | 3 | N/A |  |  |  |  | System suppliers and implementers should regularly carry out checks to ensure the valuesets/ reference sets are valid. |  | Major | Low | 3 |  | System suppliers | Transferred
Overall PRSB_NS4 | [13 empty] | Major | Medium | 3 | [7 empty] | Major | Medium | 3 |  |  | Transferred
PRSB_NS5a | 07.03.24 | Documentation burden Excessive documentation requirements can divert nurses' attention away from patient care | Healthcare professional or team using the information may miss important information and not provide appropriate treatment. | Harm to the patient – death, major injury/illness through to minor injury/ psychological distress. | The standard requires numerous detail and data points resulting in valuable time been spent on data entry. |  |  | PRSB defines data items which are Mandatory/Required/optional for users to populate. Mandatory items are kept to a minimum to deliver safe care. | Part of the standard |  |  |  |  | Major | Low | 3 |  | IT Systems should be designed to auto-populate data fields when ever appropriate. |  | User should be adequately trained to use the systems they required to use to support the provision of care. |  |  |  | Major | Low | 3 |  | System suppliers and service providers | Transferred
PRSB_NS5b |  |  |  |  | The end user having to enter the same data multiple times due to multiplicity of systems, forms etc |  |  | The standard is designed to avoid multiple entry of data by allowing re-use of information within and across systems. The standard does not address multiciplicity of systems. | Part of the standard |  |  |  |  | Major | Medium | 3 |  | IT Systems should be designed to auto-populate data fields when ever appropriate. |  | User should be adequately trained to use the systems they required to use to support the provision of care. |  |  |  | Major | Medium | 3 |  | System suppliers and service providers | Transferred
PRSB_NS5c |  |  |  |  | The end users are not adequately trained on the system and may struggle to to understand what information needs to be recorded or how to efficiently input the data. |  |  | The standard does not address user training. | [5 empty] | Major | Low | 3 |  |  |  | User should be adequately trained to use the systems they required to use to support the provision of care. |  |  |  | Major | Low | 3 |  | Service providers | Transferred
PRSB_NS5d |  |  |  |  | The end user already has demanding workloads with limited time to spend on documentation, introducing a new system may increase the time required for documentation. |  |  | The standard does not address user workload | [5 empty] | Major | Low | 3 | [5 empty] | Communication on the benefit of standard should be undertaken as part of the implementation of the standard |  | Major | Low | 3 |  | Service providers | Transferred
PRSB_NS5e |  |  |  |  | If end users are resistant to the system due to perceived added workload or lack of perceived benefit and this may lead to reduced motivation to complete documentation efficiently?? |  |  | The standard does not address change management | [5 empty] | Major | Medium | 3 | [5 empty] | Ensure change management process is taken into consideration when implementing the standard |  | Major | Low | 3 |  | Service providers | Transferred
Overall PRSB_NS5 | [13 empty] | Major | Medium | 3 | [7 empty] | Major | Medium | 3 |  |  | Transferred

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16